TIMELINE CHART / GANTT CHART

| Phase | Task Description | Priority | Duration | Start Date | End Date | Responsible |
| --- | --- | --- | --- | --- | --- | --- |
| Phase 1: Planning | Project Proposal, Requirement Gathering & Team Role Assignment | – | 1 Week | May 15, 2026 | May 21, 2026 | All Members |
| Phase 2: Analysis | SRS Documentation & User Story Mapping (Trello Backlog Setup) | – | 1 Week | May 22, 2026 | May 28, 2026 | All Members |
| Phase 3: Design | System Architecture, Database Design, UML & Wireframes | – | 2 Weeks | May 29, 2026 | Jun 11, 2026 | Shraboni, Raiyan |
| Phase 4: Sprint 1 | Admin & Student Core Modules (Login, Verification, Profile, Collaborator Search, Team Chat) | High | 2 Weeks | Jun 12, 2026 | Jun 25, 2026 | Raiyan |
| Phase 5: Sprint 2 | Professor & Researcher Core Modules (Verification, Research Lab, ORCID Sync, Partner Search) | High | 2 Weeks | Jun 26, 2026 | Jul 09, 2026 | Azraf |
| Phase 6: Sprint 3 | Industry Partner & Remaining Modules (Corporate Registration, Talent Search, Chat, Vacancies) | High | 2 Weeks | Jul 10, 2026 | Jul 23, 2026 | Sumaiya |
| Phase 7: Sprint 4 | Analytics, Announcements, Leaderboard, Notifications, Messaging & Remaining Features | Medium / Low | 2 Weeks | Jul 24, 2026 | Aug 06, 2026 | All Members |
| Phase 8: Testing | Manual Test Cases, Bug Fixing & QA Review | – | 2 Weeks | Aug 07, 2026 | Aug 20, 2026 | Sumaiya, Azraf |
| Phase 9: Review & Delivery | Documentation, Final Report Preparation & Delivery | – | 1 Week | Aug 21, 2026 | Aug 27, 2026 | Shraboni |